## Overview
Production truck monitoring — MVP 0.1 plan tracker
A one-page dashboard for the two-week, file-backed MVP. The detailed plan and architecture are in Arch/MVP_Plan_and_Architecture.docx.
At a glance
Duration | 10 working days / 2 calendar weeks |  |  | Phase | Hours | Calendar | Outcome
Effort | 58 ideal hours + 15% buffer |  |  | M0 · Contract and decisions | 7 | 2–3 days | Schema v1 + CRS agreed
Team | 1 frontend + part-time domain/design |  |  | M1 · Skeleton and shell | 6 | 1 day | App shell + map
MVP scope | JSON file → React → Leaflet map |  |  | M2 · Data layer | 10 | 2 days | Domain + file adapter
Out of scope | RSSI, Magma, MQTT, DB, auth |  |  | M3 · Map and interaction | 14 | 2–3 days | Dots + selection
Definition of done | 20 acceptance checks signed |  |  | M4 · States and polish | 10 | 2 days | States + a11y
|  |  |  | M5 · Tests and handover | 11 | 2 days | Tests + deploy
Hours by phase
Phase | Ideal hours
M0 · Contract and decisions | 7
M1 · Skeleton and shell | 6
M2 · Data layer | 10
M3 · Map and interaction | 14
M4 · States and polish | 10
M5 · Tests and handover | 11
How to use this tracker
1. Start with the Backlog sheet. Move each task from Not started to In progress to Done. The 58 hours are ideal hours, not calendar hours.
2. Use the Calendar sheet for the two-week sequence. A gate is a demo, not a status meeting.
3. Record evidence in Acceptance as you demonstrate each check. A checked box means demonstrated, not implemented.
4. Review the Risks sheet at every gate. Update probability, impact, and trigger; do not leave a risk owner blank.
5. Keep ADRs current when a decision changes. The code and the document are the source of truth, not the spreadsheet.
Status legend
Not started | In progress | Blocked | Done

## Backlog
Backlog and estimates
16 tasks, 58 ideal hours. Status values are validated; keep the Done when column testable.
ID | Phase | Task | Hours | Depends on | Owner | Status | Done when | Phase | Hours
M0-1 | M0 | Contract review with producer and customer | 4 | — | Frontend + domain | Not started | Schema v1 and sample signed off | M0
M0-2 | M0 | Coordinate and map-provider decisions | 3 | — | Frontend + domain | Not started | WGS84 confirmed; tiles/site plan chosen | M1
M1-1 | M1 | Scaffold Vite + React + TS + lint/test | 3 | — | Frontend | Not started | pnpm dev, lint, test, build work | M2
M1-2 | M1 | App shell, providers, error boundary | 3 | M1-1 | Frontend | Not started | Blank page with header/footer and no errors | M3
M2-1 | M2 | Domain types + Zod schemas + tests | 4 | M0-1 | Frontend | Not started | Valid/invalid fixtures behave as specified | M4
M2-2 | M2 | JsonFileFleetRepository + typed errors | 4 | M2-1 | Frontend | Not started | Fetch, parse, partial failure, 404 covered | M5
M2-3 | M2 | useFleetSnapshot + QueryClient | 2 | M2-2 | Frontend | Not started | Debug view updates every second
M3-1 | M3 | Map shell + station markers | 5 | M1-2 | Frontend | Not started | Map centred; stations and labels visible
M3-2 | M3 | Truck markers + status + accuracy | 5 | M3-1 | Frontend | Not started | Dots move; selected dot has a ring
M3-3 | M3 | Truck list + details panel + selection | 4 | M3-2 | Frontend | Not started | Map and list select the same object
M4-1 | M4 | Loading/empty/stale/error/partial states | 4 | M3-3 | Frontend | Not started | Every state can be triggered manually
M4-2 | M4 | Responsive layout + accessibility pass | 3 | M4-1 | Frontend + design | Not started | 1024 px and mobile; keyboard path works
M4-3 | M4 | Data health panel + diagnostics | 3 | M4-1 | Frontend | Not started | Source, age, counts, skipped records visible
M5-1 | M5 | Unit/component/integration tests | 5 | M2-2, M3-3 | Frontend | Not started | Test plan from section 9.2 is covered
M5-2 | M5 | Production build, Nginx, README, runbook | 4 | M4-2 | Frontend | Not started | Deployed URL; docs reviewed
M5-3 | M5 | Demo data, rehearsal, handover | 2 | M5-2 | Frontend + product | Not started | Demo runs twice without intervention
Total

## Calendar
Two-week calendar
Every day ends with something that can be shown. Gates are demos, not status meetings.
Day | Focus | Output | Gate
1 | Contract review; scaffold; map shell | Schema v1 agreed; Vite app; Leaflet map with site centre | G0: contract frozen
2 | Domain types, Zod, sample file, repository | Validated snapshot in tests; raw debug view | —
3 | Polling, station markers, truck dots | Moving dots from the file; last update time | G1: first dots
4 | Selection, details, status colours | Click a dot or list row; card and accuracy circle | —
5 | Error, empty, stale states; review | Demo 1; issue list; scope check | G2: usable screen
6 | Responsive layout, accessibility, diagnostics | Mobile/desktop; keyboard list; data health | —
7 | Unit, component, integration tests | Test suite green; failure cases covered | —
8 | Build, Nginx, README, runbook | Release candidate deployed at a real URL | G3: RC
9 | Bugfix, performance, demo data, rehearsal | Polished demo; 100-truck check | —
10 | Customer demo, handover, tag | Accepted MVP; v0.1.0; backlog for Phase 1 | G4: done

## Acceptance
Acceptance and release checklist
A checked box means demonstrated, not implemented. Record evidence or a link in the last column.
ID | Area | Criterion | How verified | Status | Evidence / notes
AC-01 | Map | Valid snapshot with 3 stations and 5 trucks renders within 2 s | Manual + E2E | Not started
AC-02 | Freshness | Replacing the file moves dots without a page reload | Manual + integration | Not started
AC-03 | Selection | Clicking a dot opens the correct details card | Component | Not started
AC-04 | Resilience | One invalid record is skipped; the rest render; the count is visible | Unit + component | Not started
AC-05 | Errors | Missing file shows a fatal error with Retry on first load | Component | Not started
AC-06 | Errors | Failed refresh keeps last good dots and shows a banner | Integration | Not started
AC-07 | Freshness | Old generatedAt shows a stale banner even with HTTP 200 | Unit + component | Not started
AC-08 | Performance | 100 trucks at 1 Hz remains responsive | Performance check | Not started
AC-09 | Offline | Tiles blocked: dots, stations, legend, details still work | Manual | Not started
AC-10 | Accessibility | Keyboard-only selection works through the truck list | Manual + a11y | Not started
CHK-01 | Build | Lint, typecheck, test, and production build are green | CI | Not started
CHK-02 | Deploy | Base-path deployment loads assets and data | Manual | Not started
CHK-03 | Cache | Cache-Control: no-store is present on the snapshot response | DevTools | Not started
CHK-04 | Docs | README covers run, build, deploy, and data replacement | Review | Not started
CHK-05 | Security | No secrets in the bundle; app is behind the agreed perimeter | Review | Not started
CHK-06 | Demo | Demo script rehearsed twice, including the failure drill | Rehearsal | Not started
CHK-07 | Release | Release tagged v0.1.0 with a visible build stamp | Release | Not started
CHK-08 | Contract | Example snapshot matches the v1 schema | Review | Not started
CHK-09 | Ops | Previous good snapshot and rollback path documented | Review | Not started
CHK-10 | Sign-off | Customer accepts the MVP scope and demo | Review | Not started

## Risks
Risk register
P = probability, I = impact, Score = 1–9. Review at every gate; every risk needs an owner.
Risk | P | I | Score | Mitigation | Trigger | Owner | Status
Coordinate system mismatch (local metres vs WGS84) | H | H |  | Freeze CRS; convert in producer; validate ranges; one known-point check | Dots offset by a constant distance | Frontend + domain | Open
Stale file served as live | H | H |  | Check generatedAt, not HTTP status; stale banner; external age check | HTTP 200 but positions frozen | Frontend | Open
Scope creep into RSSI/Magma/DB | H | H |  | Out-of-scope list; change rule; Phase 1/2 backlog | New must-have in standup | Product | Open
Map tiles blocked in a closed network | H | M |  | Site-plan overlay or local tiles; blank map still works | Grey tiles in the demo | IT + frontend | Open
Yandex Maps required late | M | H |  | Isolate Leaflet behind FleetMap; clarify provider on day 1 | API key mentioned after build | Product | Open
Non-atomic file write | M | H |  | Temp file + rename; previous snapshot; parse error banner | Intermittent JSON parse errors | Integrator | Open
Schema drift between producer and UI | M | M |  | Version field; Zod; contract review; example file in repo | Unknown/missing fields | Frontend + domain | Open
Performance at 1,000+ trucks | M | M |  | Canvas markers, API/WS, clustering; budget at 100 trucks | Frame drops / long tasks | Frontend | Open
Positions exposed on an open URL | M | H |  | Perimeter auth; no secrets; HTTPS; privacy review | App reachable from guest network | Security | Open
Magma integration surprises | H | M |  | Server-side adapter; Open5GS fallback; spike in Phase 2 | Events missing or API unstable | Backend | Open
Clock skew / timezone errors | M | M |  | UTC ISO strings; NTP; future-timestamp warning | “-3 s ago” or “in 2 hours” | Frontend + ops | Open
First-timer overengineering | M | M |  | One port, no Redux, no generic data source; review checklist | More abstraction than features | Tech lead | Open

## ADRs
Architecture decision records
Short, dated decisions. Update the log when a decision changes; do not leave it to memory.
ADR | Decision | Status | Date | Consequence
ADR-001 | File-backed static SPA for MVP 0.1 | Accepted | 2026-10-28 | No backend; fastest demo; file is a temporary transport
ADR-002 | FleetRepository port with a file adapter | Accepted | 2026-10-28 | Source can change without touching the UI
ADR-003 | Leaflet + OpenStreetMap for the map | Accepted | 2026-10-28 | No API key; open licence; easy markers and circles
ADR-004 | WGS84 lat/lon is the canonical UI contract | Accepted | 2026-10-28 | No geodesy in components; local metres converted upstream
ADR-005 | JSON Schema v1 + Zod at the boundary | Accepted | 2026-10-28 | Runtime safety; versioned evolution
ADR-006 | 1 Hz polling, not WebSocket, in MVP | Accepted | 2026-10-28 | Simple, debuggable, proxy-friendly; upgrade later
ADR-007 | No database or history in MVP | Accepted | 2026-10-28 | Smaller scope; live dots only
ADR-008 | Magma only server-side in Phase 2 | Accepted | 2026-10-28 | No credentials or core APIs in the browser

## Contract
Snapshot contract v1.0 — field reference
The complete contract is docs/data-contract.md. This sheet is a quick field lookup for the producer.
Section | Field | Type | Required | Rules
Top level | schemaVersion | string | yes | 1.x; major mismatch is fatal
Top level | generatedAt | ISO 8601 | yes | UTC with Z or offset; when the snapshot was made
Top level | site | object | yes | Site identity and map centre
Top level | baseStations | array | yes | 0+ station objects
Top level | trucks | array | yes | 0+ truck objects; empty is valid
Site | id | string | yes | Stable site ID
Site | name | string | yes | Header label
Site | center.lat | number | yes | WGS84, -90..90
Site | center.lon | number | yes | WGS84, -180..180
Site | defaultZoom | integer | yes | 2..22; 16–18 typical
Site | timeZone | IANA string | no | Default: browser zone
Site | map | object | no | mode osm ¦ image ¦ blank
Station | id | string | yes | Stable, unique
Station | name | string | yes | Map label
Station | lat, lon | number | yes | WGS84
Station | status | enum | yes | online ¦ offline ¦ maintenance
Station | heightM | number | no | Antenna height; not used for 2D
Truck | id | string | yes | Stable, unique; never an array index
Truck | name | string | no | Fallback to id
Truck | lat, lon | number | yes | WGS84
Truck | updatedAt | ISO 8601 | yes | When this truck was measured
Truck | status | enum | yes | moving ¦ idle ¦ offline ¦ unknown
Truck | accuracyM | number | no | Radius in metres, >= 0; absent = unknown
Truck | method | string | no | Known values labelled; unknown raw
Truck | speedMps | number | no | Metres per second, >= 0
Truck | headingDeg | number | no | 0..<360; 0 = north
Truck | zone | string | no | Future grouping
Truck | batteryPct | number | no | 0..100